## Homepage
TWENTY ONE JEWELS | [6 empty] | TWENTY ONE JEWELS
Version: |  |  | Environmental Details : Windows 10 |  | Tested By : Chandana J S
Verified By: Pradeep K C |  |  | Module Name : Home Page |  | Date : 28/02/2024
Test Id | Test Description | Test Procedure | Test Data | Expected Result | Actual Result | Result | Screenshot
Ty_Js_01 | Check whether the application link is working properly or not | 1.Open TwentyOneJewels Website |  | The website link for TwentyOneJewels website should work properly and page should be opened without any errors | The website link for TwentyOneJewels website is working properly and page should is opening without any errors | Pass
Ty_Js_02 | Check whether the application works in low internet connection | 1.Open TwentyOneJewels Website 2.Enter Test Data | Input the Internet connectivity less than 30kps | The Website should open up even though the internet connectivity is slow. | The Website is opening up even though the internet connectivity is slow. | Pass
Ty_Js_03 | Check whether the logo is placed right and is visible or not | 1.Open TwentyOneJewels Website 2.Locate Logo |  | The logo should be placed right and should be visible | The logo is placed right and visible | Pass
Ty_Js_04 | Check whether the Homepage option is appearing and it navigate to its corresponding page whenever we click on logo | 1.Open TwentyOneJewels Website 2.Click on Logo |  | The Homepage option should appear and it should navigate to its corresponding page whenever we click on logo | The Homepage option is appearing and it is navigating to its corresponding page whenever we click on logo | Pass
Ty_Js_05 | Check whether country currency dropdown is active or not | 1.Open TwentyOneJewels Website 2.Click on Logo 3.Click on Country Currency Dropdown |  | Country Currency dropdown should be active | Country Currency dropdown is active | Pass
Ty_Js_06 | Check whether the currency layout changes according to our selection or not. | 1.Open TwentyOneJewels Website 2.Click on Home 3.Click on Test Data | GBP | The currency layout should change according to our selection | The currency layout is changing according to our selection | Pass
Ty_Js_07 | Check whether the search bar is working or not | 1.Open TwentyOneJewels Website 2.Click on Search Bar 3.Enter Test Data 4.Click Search | Earring | Search bar should be working properly | Search bar is working properly | Pass
Ty_Js_08 | Check whether the search bar shows search not found if we given invalid search or not | 1.Open TwentyOneJewels Website 2.Click on Search Bar 3.Enter Invalid Test Data 4.Click Search | Brush | Search bar should show search not found if we give invalid searches | Search bar is showing search not found if we give invalid searches | Pass
Ty_Js_09 | Check whether account button is active or not | 1.Open TwentyOneJewels Website 2.Click Account option |  | Account button should be active | Account button is not active | Fail | https://drive.google.com/file/d/1Ty3LTOD6io-GdlTtKn8zl0es9BoY7_zj/view?usp=sharing
Ty_Js_10 | Check whether account button redirect to next page or not | 1.Open TwentyOneJewels Website 2.Click Account option |  | Account button should redirect to next page | Account button is not redirecting to next page | Fail | https://drive.google.com/file/d/1Ty3LTOD6io-GdlTtKn8zl0es9BoY7_zj/view?usp=sharing
Ty_Js_11 | Check whether cart button is active or not | 1.Open TwentyOneJewels Website 2.Click Cart Option |  | Cart button should be active | Cart button is active | Pass
Ty_Js_12 | Check whether place order button is visible while selection or not | 1.Open TwentyOneJewels Website 2.Click Cart Option 3.Locate Place Order Button |  | Place order button should be visible while selection | Place order button is not visible while selection | Fail | https://drive.google.com/file/d/1TCIFmeK20EfF0LGx6F55pVVhLeLFOCQj/view?usp=sharing
Ty_Js_13 | Check whether place order button redirect to next page if cart is empty or not | 1.Open TwentyOneJewels Website 2.Click Cart Option 3.Click Place Order Button |  | Place order button should not redirect to next page | Place order button is redirecting to next page | Fail | https://drive.google.com/file/d/1OmuqhJAEwjMvaVfSYZ6rsUFe8TOPmeJM/view?usp=sharing
Ty_Js_14 | Check whether shop by category dropdown is active or not | 1.Open TwentyOneJewels Website 2.Click Logo 3.Locate Shop by Category Dropdown |  | Shop by category dropdown should be active | Shop by category dropdown is active | Pass
Ty_Js_15 | Check whether shop by collection dropdown is active or not | 1.Open TwentyOneJewels Website 2.Click Logo 3.Locate Shop by Collection Dropdown |  | Shop by collection dropdown should be active | Shop by collection dropdown is active | Pass
Ty_Js_16 | Check whether All Time Bestseller option is active or not | 1.Open TwentyOneJewels Website 2.Click Logo 3.Locate All Time Bestseller Option |  | All Time Bestseller option should be active | All Time Bestseller option is active | Pass
Ty_Js_17 | Check whether The Big Sale option is active or not | 1.Open TwentyOneJewels Website 2.Click Logo 3.Locate The Big Sale Option |  | The Big Sale option should be active | The Big Sale option is active | Pass
Ty_Js_18 | Check whether Valentines Exclusive is active or not | 1.Open TwentyOneJewels Website 2.Click Logo 3.Locate Valentines Exclusive |  | Valentines is Exclusive should be active | Valentines Exclusive option is active | Pass
Ty_Js_19 | Check whether View Full Collection button is active or not | 1.Open TwentyOneJewels Website 2.Click Logo 3.Click View Full Collection Button |  | View Full Collection button should be active | View Full Collection button is active | Pass
Ty_Js_20 | Check whether View Full Collection button navigates to its corresponding page or not | 1.Open TwentyOneJewels Website 2.Click Logo 3.Click View Full Collection Button |  | View Full Collection button should navigates to its corresponding page | View Full Collection button is navigating to its corresponding page | Pass
Ty_Js_21 | Check whether View All button is active or not | 1.Open TwentyOneJewels Website 2.Click Logo 3.Click View All Button |  | View All button should be active | View All button is active | Pass
Ty_Js_22 | Check whether View All button navigates to its corresponding page or not | 1.Open TwentyOneJewels Website 2.Click Logo 3.Click View All Button |  | View All button should navigates to its corresponding page | View All button is navigating to its corresponding page | Pass
Ty_Js_23 | Check Pick your Evil eye button is visible while selection or not | 1.Open TwentyOneJewels Website 2.Click Logo 3.Locate Pick ur Evil Eye Button |  | Place order button should be visible while selection | Place order button is not visible while selection | Fail | https://drive.google.com/file/d/13CGvQcHMcii9kX9JZHz8dSuZwrpZ8LBh/view?usp=sharing
Ty_Js_24 | Check Pick your Evil eye button redirects to its corresponding page or not | 1.Open TwentyOneJewels Website 2.Click Logo 3.Click Pick ur Evil Eye Button |  | Pick your Evil eye button should redirects to its corresponding page | Pick your Evil eye button is redirecting to its corresponding page | Pass
Ty_Js_25 | Check whether side arrow for window slide is working properly or not | 1.Open TwentyOneJewels Website 2.Click Logo 3.Locate View Full Collection Image |  | Side arrows for window slide should work properly | Side arrows for window slide is not working properly | Fail | https://drive.google.com/file/d/17gPSHNfA_9w5t_r_UJMGa-pOW9b6t4CL/view?usp=sharing
Ty_Js_26 | Check whether each item navigate to its respective pages when we select one item or not | 1.Open TwentyOneJewels Website 2.Click Logo 3.Click Any one of the Item |  | Each item should navigate to its respective pages when we select one item | Each item is navigating to its respective pages when we select one item | Pass
Ty_Js_27 | Check whether item shows unavailable when it is out of stock or not | 1.Open TwentyOneJewels Website 2.Click Logo 3.Click Any one of the Item that is unavailable |  | Item should show unavailable when it is out of stock | Item is showing unavailable when it is out of stock | Pass
Ty_Js_28 | Check Connect with priyanka button is visible while selection or not | 1.Open TwentyOneJewels Website 2.Click Logo 3.Locate Connect with priyanka Button |  | Connect with priyanka button should be visible while selection | Connect with priyanka button is not visible while selection | Fail | https://drive.google.com/file/d/1FJsqmaKYZnfxyttB5IAqYqYvgukfDE87/view?usp=sharing
Ty_Js_29 | Check Connect with priyanka button redirects to its next page or not | 1.Open TwentyOneJewels Website 2.Click Logo 3.Click Connect with priyanka Button |  | Connect with priyanka button should redirects to its next page | Connect with priyanka button is not redirecting to its next page | Fail | https://drive.google.com/file/d/1u_KnvRQZkJO8A6A5A6h4OsbDVKHup1n7/view?usp=sharing
Ty_Js_30 | Check Get directions button is visible while selection or not | 1.Open TwentyOneJewels Website 2.Click Logo 3.Locate Get Directions Button |  | Get directions button should be visible while selection | Get directions button is not visible while selection | Fail | https://drive.google.com/file/d/1-XXMdEdFfRpYXWMgeCKz7VOrPPqGQl6m/view?usp=sharing
Ty_Js_31 | Check Get directions button redirects to map page or not | 1.Open TwentyOneJewels Website 2.Click Logo 3.Click Get Directions Button |  | Get directions button should redirects to map page | Get directions button is redirecting to map page | Pass
Ty_Js_32 | Check Get directions button is giving correct direction or location with respect to store address or not | 1.Open TwentyOneJewels Website 2.Click Logo 3.Click Get Directions Button |  | Get directions button should give correct direction or location with respect to store address | Get directions button is not giving correct direction or location with respect to store address | Fail | https://drive.google.com/file/d/1zHuBeaTmAMuizHWIFlZ_8LO4qif5ckVP/view?usp=sharing
Ty_Js_33 | Check whether About us page redirects to its respective page or not | 1.Open TwentyOneJewels Website 2.Click Logo 3.Click About Us page |  | About us page should redirect to its respective page | About us page is redirecting to its respective page | Pass
Ty_Js_34 | Check whether Contact us page redirects to its respective page or not | 1.Open TwentyOneJewels Website 2.Click Logo 3.Click Contact Us page |  | Contact us page should redirects to its respective page | Contact us page is redirecting to its respective page | Pass
Ty_Js_35 | Check whether Name field in Contact us page active or not | 1.Open TwentyOneJewels Website 2.Click Logo 3.Click Contact Us page 4.Enter Test Data | Abhi | Name field in Contact us page should be active | Name field in Contact us page is active | Pass
Ty_Js_36 | Check whether Name field in Contact us page accepts alphabets or not | 1.Open TwentyOneJewels Website 2.Click Logo 3.Click Contact Us page 4.Enter Test Data | Tom | Name field in Contact us page should accepts alphabets | Name field in Contact us page is accepting alphabets | Pass
Ty_Js_37 | Check whether Name field in Contact us page accepts special characters or not | 1.Open TwentyOneJewels Website 2.Click Logo 3.Click Contact Us page 4.Enter Test Data | !$ | Name field in Contact us page should not accept special characters | Name field in Contact us page is accepting special characters | Fail | https://drive.google.com/file/d/1ayb_elxCAZ8m_-j0hTV6C2j5lAIsfsVk/view?usp=sharing
Ty_Js_38 | Check whether Name field in Contact us page accepts numbers or not | 1.Open TwentyOneJewels Website 2.Click Logo 3.Click Contact Us page 4.Enter Test Data | q577 | Name field in Contact us page should not accept numbers | Name field in Contact us page is accepting numbers | Fail | https://drive.google.com/file/d/1yBYW0BIpnAvcU74kGzFPB6UFH4QiEEWO/view?usp=sharing
Ty_Js_39 | Check whether Name field in Contact us page accepts empty field or not | 1.Open TwentyOneJewels Website 2.Click Logo 3.Click Contact Us page 4.Enter Test Data except name field | 1.sdcfvgbh@gmail.com 2.562 3.sdxcfgvbhn | Name field in Contact us page should not accepts empty field | Name field in Contact us page is accepting empty field | Fail | https://drive.google.com/file/d/1efJKhZQmT4ezyIpALNmKzNQV6wxmWix-/view?usp=sharing
Ty_Js_40 | Check whether Email field in Contact us page active or not | 1.Open TwentyOneJewels Website 2.Click Logo 3.Click Contact Us page 4.Locate Email field 5.Enter test data | 234dfg@gmail.com | Email field in Contact us page should be active | Email field in Contact us page is active | Pass
Ty_Js_41 | Check whether Email field in Contact us page accepts only email format or not | 1.Open TwentyOneJewels Website 2.Click Logo 3.Click Contact Us page | dcfvgbhnj345@gmail.com | Email field in Contact us page should accepts only email format | Email field in Contact us page is accepting only email format | Pass
Ty_Js_42 | Check whether Phone Number in Contact us page active or not | 1.Open TwentyOneJewels Website 2.Click Logo 3.Click Contact Us page 4.Locate PhoneNumber field 5.Enter test data | 24567 | Phone Number in Contact us page should be active | Phone Number in Contact us page is active | Pass
Ty_Js_43 | Check whether Phone Number in Contact us page accept characters other than numbers or not | 1.Open TwentyOneJewels Website 2.Click Logo 3.Click Contact Us page 4.Locate PhoneNumber field 5.Enter test data | 45678dfcgh | Phone Number in Contact us page should not accept characters other than numbers | Phone Number in Contact us page is not accepting characters other than numbers | Pass
Ty_Js_44 | Check whether Phone Number in Contact us page accept numbers less than 9 digits or not | 1.Open TwentyOneJewels Website 2.Click Logo 3.Click Contact Us page 4.Locate PhoneNumber field 5.Enter test data | 12 | Phone Number in Contact us page should not accept numbers less than 9 digits | Phone Number in Contact us page is accepting numbers less than 9 digits | Fail | https://drive.google.com/file/d/1C4zPlcV_p_tWHYGl1YUhVI2DnUaLrMJt/view?usp=sharing
Ty_Js_45 | Check whether Messages in Contact us page active or not | 1.Open TwentyOneJewels Website 2.Click Logo 3.Click Contact Us page 4.Locate Messages 5.Enter test data | sxdcfgvhjk2345 | Messages in Contact us page should be active | Messages in Contact us page is active | Pass
Ty_Js_46 | Check whether Send button in Contact us page active or not | 1.Open TwentyOneJewels Website 2.Click Logo 3.Locate Send Button |  | Send button in Contact us page should be active | Send button in Contact us page is active | Pass
Ty_Js_47 | Check whether Messages in Contact us page accepts all characters or not | 1.Open TwentyOneJewels Website 2.Click Logo 3.Click Contact Us page 4.Locate Messages 5.Enter test data | edrwt234&* | Messages in Contact us page should accepts all characters | Messages in Contact us page is accepting all characters | Pass
Ty_Js_48 | Check Send button is visible while selection or not | 1.Open TwentyOneJewels Website 2.Click Logo 3.Locate Send Button |  | Send button should be visible while selection | Send button is not visible while selection | Fail | https://drive.google.com/file/d/10zFnAQnXHAssbFmbC9XAkCTzaHXJY4-o/view?usp=sharing
Ty_Js_49 | Check Send button is active with empty fields or not | 1.Open TwentyOneJewels Website 2.Click Logo 3.Click Send Button |  | Send button should not be active with empty fields | Send button is active with empty fields | Fail | https://drive.google.com/file/d/1Q_WzuIhB2GdzK_aK_eckae7ZgJOzQ2Zb/view?usp=sharing
Ty_Js_50 | Check whether Jewelry Care page redirects to its respective page or not | 1.Open TwentyOneJewels Website 2.Click Logo 3.Click Jewelry Care |  | Jewelry page should redirects to its respective page | Jewelry page is redirecting to its respective page | Pass
Ty_Js_51 | Check whether FAQs page redirects to its respective page or not | 1.Open TwentyOneJewels Website 2.Click Logo 3.Click FAQs |  | FAQs page should redirects to its respective page | FAQs page is redirecting to its respective page | Pass
Ty_Js_52 | Check whether Delivery & Exchange/ Returns & Refunds page redirects to its respective page or not | 1.Open TwentyOneJewels Website 2.Click Logo 3.Click Delivery & Exchange/ Returns & Refunds |  | Delivery & Exchange/ Returns & Refunds page should redirects to its respective page | Delivery & Exchange/ Returns & Refunds page is redirecting to its respective page | Pass
Ty_Js_53 | Check whether Privacy Policy page redirects to its respective page or not | 1.Open TwentyOneJewels Website 2.Click Logo 3.Click Privacy Policy |  | Privacy Policy should redirects to its respective page | Privacy Policy page is redirecting to its respective page | Pass
Ty_Js_54 | Check whether Terms & Conditions page redirects to its respective page or not | 1.Open TwentyOneJewels Website 2.Click Logo 3.Click Terms & Conditions |  | Terms & Conditions page should redirects to its respective page | Terms & Conditions page is redirecting to its respective page | Pass
Ty_Js_55 | Check whether Loyalty Program page redirects to its respective page or not | 1.Open TwentyOneJewels Website 2.Click Logo 3.Click Loyalty Program |  | Loyalty Program page should redirects to its respective page | Loyalty Program page is redirecting to its respective page | Pass
Ty_Js_56 | Check whether Terms of Service page redirects to its respective page or not | 1.Open TwentyOneJewels Website 2.Click Logo 3.Click Terms of Service |  | Terms of Service page should redirects to its respective page | Terms of Service page is redirecting to its respective page | Pass
Ty_Js_57 | Check whether facebook link page redirects to its respective page or not | 1.Open TwentyOneJewels Website 2.Click Logo 3.Click Facebook Link |  | Facebook Link page should redirects to its respective page | Facebook Link page is redirecting to its respective page | Pass
Ty_Js_58 | Check whether instagram link page redirects to its respective page or not | 1.Open TwentyOneJewels Website 2.Click Logo 3.Click Instagram Link |  | Instagram Link page should redirects to its respective page | Instagram Link page is redirecting to its respective page | Pass
Ty_Js_59 | Check whether pinterest link page redirects to its respective page or not | 1.Open TwentyOneJewels Website 2.Click Logo 3.Click Pinterest Link |  | Pinterest Link page should redirects to its respective page | Pinterest Link page is redirecting to its respective page | Pass
Ty_Js_60 | Check whether join our mailing list field is active or not | 1.Open TwentyOneJewels Website 2.Click Logo 3.Locate Mailing List Field |  | Join our mailing list field should be active | Join our mailing list field is active | Pass
Ty_Js_61 | Check whether join our mailing list field accept email format only or not | 1.Open TwentyOneJewels Website 2.Click Logo 3.Locate Mailing List Field 4.Enter Test Data | aswdfrgt23@gmail.com | Join our mailing list field should accept email format only | Join our mailing list field is accepting email format only | Pass

## Category &Collection
TWENTY ONE JEWELS
Version: |  |  | Environmental Details : Windows 10 |  |  | Tested By : Chandana J S
Verified By:Pradeep KC |  |  | Module Name : Home Page | : Category & Collection |  | Date :28/02/2024
Test Id | Test Description | Test Procedure | Test Data | Expected Result | Actual Result | Results | Screenshots
Ty_Js_01 | Check whether Explore All page is active or not | 1.Open TwentyOneJewels Website 2.Locate Shop By Collection 3.Click Explore All |  | Explore All page should be active | Explore All page is active | Pass
Ty_Js_02 | Check whether Explore All page expands when we select explore all or not | 1.Open TwentyOneJewels Website 2.Locate Shop By Collection 3.Click Explore All |  | Explore All page should expands when we select explore all | Explore All page is expanding when we select explore all | Pass
Ty_Js_03 | Check whether Filter dropdown is working properly in Explore All page or not | 1.Open TwentyOneJewels Website 2.Locate Shop By Collection 3.Click Explore All 4.Locate Filter Dropdown |  | Filter dropdown should work properly in Explore All page | Filter dropdown is working properly in Explore All page | Pass
Ty_Js_04 | Check whether Filter dropdown options have any spell check errors or not | 1.Open TwentyOneJewels Website 2.Locate Shop By Collection 3.Click Explore All 4.Click Filter Dropdown |  | Filter dropdown options should not have any spell check errors | Filter dropdown options is having spell check errors | Fail | https://drive.google.com/file/d/15YVGRFit_Jsl_4FOgdl6cyBQrSU2CZZs/view?usp=sharing
Ty_Js_05 | Check whether Filter dropdown options is in alphabetically arranged format or not | 1.Open TwentyOneJewels Website 2.Locate Shop By Collection 3.Click Explore All 4.Click Filter Dropdown |  | Filter dropdown options should be in alphabetically arranged format | Filter dropdown options is not in alphabetically arranged format | Fail | https://drive.google.com/file/d/1QWX9UbmcOzdxo4AStLys0WYYipyrIRWu/view?usp=sharing
Ty_Js_06 | Check whether Filter dropdown options navigates to its respective pages after seletion or not | 1.Open TwentyOneJewels Website 2.Locate Shop By Collection 3.Click Explore All 4.Click Filter Dropdown 5.Select BestSeller |  | Filter dropdown options should navigates to its respective pages after selection | Filter dropdown options is navigating to its respective pages after selection | Pass
Ty_Js_07 | Check whether sort dropdown is working properly in Explore All page or not | 1.Open TwentyOneJewels Website 2.Locate Shop By Collection 3.Click Explore All 4.Locate Sort Dropdown |  | Sort dropdown should work properly in Explore All page | Sort dropdown is working properly in Explore All page | Pass
Ty_Js_08 | Check whether Price high to low option sorts and display items according to its respective option or not | 1.Open TwentyOneJewels Website 2.Locate Shop By Collection 3.Click Explore All 4.Locate Sort Dropdown 5.Click Price high to low |  | Price high to low option should sorts and display items according to its respective option | Price high to low option sorts and display items according to its respective option | Pass
Ty_Js_09 | Check whether Price low-high option sorts and display items according to its respective option or not | 1.Open TwentyOneJewels Website 2.Locate Shop By Collection 3.Click Explore All 4.Locate Sort Dropdown 5.Click Price low to high |  | Price low to high option should sorts and display items according to its respective option | Price low to high option sorts and display items according to its respective option | Pass
Ty_Js_10 | Check whether Alphabetically A-Z option sorts and display items according to its respective option or not | 1.Open TwentyOneJewels Website 2.Locate Shop By Collection 3.Click Explore All 4.Locate Sort Dropdown 5.Click Alphabetically A-Z |  | Alphabetically A-Z option should sorts and display items according to its respective option | Alphabetically A-Z is not sorting and displaying items according to its respective option | Fail | https://drive.google.com/file/d/1Q0KvBPh-tqCICekrCLy1tlTt7WH0mk3P/view?usp=sharing
Ty_Js_11 | Check whether Alphabetically Z-A option sorts and display items according to its respective option or not | 1.Open TwentyOneJewels Website 2.Locate Shop By Collection 3.Click Explore All 4.Locate Sort Dropdown 5.Click Alphabetically Z-A |  | Alphabetically Z-A should sorts and display items according to its respective option | Alphabetically Z-A is sorting and displaying items according to its respective option | Pass
Ty_Js_12 | Check whether Date old to new option sorts and display items according to its respective option or not | 1.Open TwentyOneJewels Website 2.Locate Shop By Collection 3.Click Explore All 4.Locate Sort Dropdown 5.Click Date old to new |  | Date old to new option should sorts and display items according to its respective option | Date old to new option sorts and display items according to its respective option | Pass
Ty_Js_13 | Check whether Date new to old option sorts and display items according to its respective option or not | 1.Open TwentyOneJewels Website 2.Locate Shop By Collection 3.Click Explore All 4.Locate Sort Dropdown 5.Click Date new to old |  | Date new to old option should sorts and display items according to its respective option | Date new to old option sorts and display items according to its respective option | Pass
Ty_Js_14 | Check whether Best Selling option sorts and display items according to its respective option or not | 1.Open TwentyOneJewels Website 2.Locate Shop By Collection 3.Click Explore All 4.Locate Sort Dropdown 5.Click Best Selling |  | BestSelling option should sorts and display items according to its respective option | BestSelling option sorts and display items according to its respective option | Pass
Ty_Js_15 | Check whether Unavailable item shows out of stock option or not | 1.Open TwentyOneJewels Website 2.Locate Shop By Collection 3.Click Explore All 4.Select an Item which is unavailable | Zivaya Diamond Party Earrings | Unavailable item should shows out of stock option | Unavailable item is showing out of stock option | Pass
Ty_Js_16 | Check whether Zoom in option works properly for each item or not | 1.Open TwentyOneJewels Website 2.Locate Shop By Collection 3.Click Explore All 4.Select an Item 5.Click Zoom in |  | Zoom in option should work properly for each item | Zoom in option is working properly for each item | Pass
Ty_Js_17 | Check whether Images of items is selectable or not | 1.Open TwentyOneJewels Website 2.Locate Shop By Collection 3.Click Explore All 4.Select an Item 5.Click on multiple images of the item |  | Images of items should selectable | Images of item is selectable | Pass
Ty_Js_18 | Check whether Share to Facebook page link is working properly or not | 1.Open TwentyOneJewels Website 2.Locate Shop By Collection 3.Click Explore All 4.Select an Item 5.Click Share to Facebook link |  | Share to Facebook page link should work properly | Share to Facebook page link is working properly | Pass
Ty_Js_19 | Check whether Share to Twitter page link is working properly or not | 1.Open TwentyOneJewels Website 2.Locate Shop By Collection 3.Click Explore All 4.Select an Item 5.Click Share to Twitter link |  | Share to Twitter page link should work properly | Share to Twitter page link is working properly | Pass
Ty_Js_20 | Check whether Share to Pinterest page link is working properly or not | 1.Open TwentyOneJewels Website 2.Locate Shop By Collection 3.Click Explore All 4.Select an Item 5.Click Share to Pinterest link |  | Share to Pinterest page link should work properly | Share to Pinterest page link is working properly | Pass
Ty_Js_21 | Check whether add to cart button is active or not | 1.Open TwentyOneJewels Website 2.Locate Shop By Collection 3.Click Explore All 4.Select an Item 5.Locate Add to Cart |  | add to cart button should be active | add to cart button is active | Pass
Ty_Js_22 | Check whether add to cart button adds items to cart or not | 1.Open TwentyOneJewels Website 2.Locate Shop By Collection 3.Click Explore All 4.Select an Item 5.Click Add to Cart |  | Add to cart button should add items to cart | Add to cart button is adding items to cart | Pass
Ty_Js_23 | Check whether Buy now button is active or not | 1.Open TwentyOneJewels Website 2.Locate Shop By Collection 3.Click Explore All 4.Select an Item 5.Locate Buy Now |  | Buy now button should be active | Buy now button is active | Pass
Ty_Js_24 | Check whether Buy now button redirects to cart page or not | 1.Open TwentyOneJewels Website 2.Locate Shop By Collection 3.Click Explore All 4.Select an Item 5.Click Buy Now |  | Buy now button should redirects to cart page | Buy now button is redirecting to cart page | Pass
Ty_Js_25 | Check whether All item has prices greater than zero or not | 1.Open TwentyOneJewels Website 2.Locate Shop By Collection 3.Click Explore All 4.Select an Item | Yes I do Multi Coloured Gold Finish Pendant with Chain | All item should have prices greater than zero | All item is not having prices greater than zero | Fail | https://drive.google.com/file/d/1uRJSJn4g3idMIRIM2k2hko56sJOgCGsT/view?usp=sharing
Ty_Js_26 | Check whether Next option navigates to next page or not | 1.Open TwentyOneJewels Website 2.Locate Shop By Collection 3.Click Explore All 4.Click Next Item |  | Next option should navigates to next page | Next option is navigating to next page | Pass
Ty_Js_27 | Check whether Previous option navigates to previous page or not | 1.Open TwentyOneJewels Website 2.Locate Shop By Collection 3.Click Explore All 4.Click Previous Item |  | Previous option should navigates to next page | Previous option is navigating to previous page | Pass
Ty_Js_28 | Check whether Everyday option navigates to its respective pages or not | 1.Open TwentyOneJewels Website 2.Locate Shop By Collection 3.Click Explore All 4.Click Everyday option |  | Everyday option should navigates to its respective pages | Everyday option is navigating to its respective pages | Pass
Ty_Js_29 | Check whether DailyWearPendant option navigates to its respective pages or not | 1.Open TwentyOneJewels Website 2.Locate Shop By Collection 3.Click Explore All 4.Click DailyWearPendant option |  | DailyWearPendant option should navigates to its respective pages | DailyWearPendant option is navigating to its respective pages | Pass
Ty_Js_30 | Check whether EverydayPendants option navigates to its respective pages or not | 1.Open TwentyOneJewels Website 2.Locate Shop By Collection 3.Click Explore All 4.Click Everyday Pendants option |  | EverydayPendants option should navigates to its respective pages | EverydayPendants option is navigating to its respective pages | Pass
Ty_Js_31 | Check whether LongEarrings option navigates to its respective pages or not | 1.Open TwentyOneJewels Website 2.Locate Shop By Collection 3.Click Explore All 4.Click Long Earrings option |  | LongEarrings option should navigates to its respective pages | LongEarringsoption is navigating to its respective pages | Pass
Ty_Js_32 | Check whether Necklace set option navigates to its respective pages or not | 1.Open TwentyOneJewels Website 2.Locate Shop By Collection 3.Click Explore All 4.Click Necklace set option |  | Necklace set option should navigates to its respective pages | Necklace setoption is navigating to its respective pages | Pass
Ty_Js_33 | Check whether Bracelets option navigates to its respective pages or not | 1.Open TwentyOneJewels Website 2.Locate Shop By Collection 3.Click Explore All 4.Click Bracelets option |  | Bracelets option should navigates to its respective pages | Bracelets optionoption is navigating to its respective pages | Pass
Ty_Js_34 | Check whether Rings option navigates to its respective pages or not | 1.Open TwentyOneJewels Website 2.Locate Shop By Collection 3.Click Explore All 4.Click Ring option |  | Rings option should navigates to its respective pages | Ringsoption is navigating to its respective pages | Pass
Ty_Js_35 | Check whether Full Collection option navigates to its respective pages or not | 1.Open TwentyOneJewels Website 2.Locate Shop By Collection 3.Click Explore All 4.Click Full Collection option |  | Full Collection option should navigates to its respective pages | Full Collectionoption is navigating to its respective pages | Pass
Ty_Js_36 | Check whether Summer2023 option navigates to its respective pages or not | 1.Open TwentyOneJewels Website 2.Locate Shop By Collection 3.Click Explore All 4.Click Summer2023 option |  | Summer2023 option should navigates to its respective pages | Summer2023 option is navigating to its respective pages | Pass
Ty_Js_37 | Check whether WorkWear Collection option navigates to its respective pages or not | 1.Open TwentyOneJewels Website 2.Locate Shop By Collection 3.Click Explore All 4.Click Workwear option |  | WorkWear Collection option should navigates to its respective pages | WorkWear Collection option is navigating to its respective pages | Pass
Ty_Js_38 | Check whether Kids Range option navigates to its respective pages or not | 1.Open TwentyOneJewels Website 2.Locate Shop By Collection 3.Click Explore All 4.Click Kids Range option |  | Kids Range option should navigates to its respective pages | Kids Rangeoption is navigating to its respective pages | Pass
Ty_Js_39 | Check whether Combo offer option navigates to its respective pages or not | 1.Open TwentyOneJewels Website 2.Locate Shop By Collection 3.Click Explore All 4.Click Combo offer option |  | Combo offer option should navigates to its respective pages | Combo offeroption is navigating to its respective pages | Pass
Ty_Js_40 | Check whether Indian rangeoption navigates to its respective pages or not | 1.Open TwentyOneJewels Website 2.Locate Shop By Collection 3.Click Explore All 4.Click Indian range option |  | Indian range option should navigates to its respective pages | Indian rangeoption is navigating to its respective pages | Pass
Ty_Js_41 | Check whether Rose gold collection option navigates to its respective pages or not | 1.Open TwentyOneJewels Website 2.Locate Shop By Collection 3.Click Explore All 4.Click Rose gold option |  | Rose gold collection option should navigates to its respective pages | Rose gold collectionoption is navigating to its respective pages | Pass
Ty_Js_42 | Check whether Ruby Love option navigates to its respective pages or not | 1.Open TwentyOneJewels Website 2.Locate Shop By Collection 3.Click Explore All 4.Click Ruby Love option |  | Ruby Love option should navigates to its respective pages | Ruby Love option is navigating to its respective pages | Pass

## Collection Pages
TWENTY ONE JEWELS
Version: |  |  | Environmental Details : Windows 10 |  | Tested By:Chandana J S
Verified By: Pradeep K C |  |  | Module Name:Collection Pages |  | Date: | Date:28/02/2024
Test Id | Test Description | Test Procedure | Test Data | Expected Result | Actual Result | Result | Screenshots
Ty_Js_01 | Check whether all the items has images of the item displayed or not | 1.Open TwentyOneJewels Website 2.Locate All Time Best Seller 3.Click Light Range mini halo ruby studs | Light Range mini halo ruby studs | All the items should have images of the item displayed | All the items is not having images of the item displayed | Fail | https://drive.google.com/file/d/1K0MFlfsLqNToNv77lcfPmeWcFsByAhvI/view?usp=sharing
Ty_Js_02 | Check whether all the items has images of the item displayed or not | 1.Open TwentyOneJewels Website 2.Locate All Time Best Seller 3.Click Light range 40 Cent solatitare on pure 925 Silver | Light range 40 Cent solatitare on pure 925 Silver | All the items should have images of the item displayed | All the items is not having images of the item displayed | Fail | https://drive.google.com/file/d/189oNGDDPpyzL8EQJLTQ94xpmjrLnAWMY/view?usp=sharing
Ty_Js_03 | Check whether duplication of option is there in filter dropdown or not | 1.Open TwentyOneJewels Website 2.Locate All Time Best Seller 3.Click Filter DropDown |  | Duplication of option should not be there in filter dropdown | Duplication of option is there in filter dropdown | Fail | https://drive.google.com/file/d/1gVK7SfJUVMGOfeUTDouJ8ens5VQ57iTp/view?usp=sharing
Ty_Js_04 | Check whether description of the item is different for each one or not | 1.Open TwentyOneJewels Website 2.Locate All Time Best Seller 3.Click an Item |  | Description of the item should be different for each one | Description of the item is different for each one | Pass
Ty_Js_05 | Check whether description of each group of item is different for each one or not | 1.Open TwentyOneJewels Website 2.Locate All Time Best Seller 3.Click a group of Item | Rings | Description of each group of item should be different for each one | Description of each group of item is different for each one | Pass
Ty_Js_06 | Check whether each option in filter dropdown redirect to each pages or not | 1.Open TwentyOneJewels Website 2.Locate All Time Best Seller 3.Click Filter Dropdown 4.Click sale on dropdown | Sales | Each option in filter dropdownshould redirect to each pages | Each option in filter dropdown is not redirecting to each pages | Fail | https://drive.google.com/file/d/10wu6a2Nerv8HHekF42lbdUlFD9HxmpDX/view?usp=sharing
Ty_Js_07 | Check whether The Big Sale page redirects to its respective page or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page |  | The Big Sale page should redirects to its respective page | The Big Sale page is redirecting to its respective page | Pass
Ty_Js_08 | Check whether Valentines Exclusive page redirects to its respective page or not | 1.Open TwentyOneJewels Website 2.Click Valentines Exclusive page |  | Valentines Exclusive page should redirects to its respective page | Valentines Exclusive page is redirecting to its respective page | Pass
Ty_Js_09 | Check whether dropdown in Valentines Exclusive page is working or not | 1.Open TwentyOneJewels Website 2.Click Valentines Exclusive page |  | Dropdown in Valentines Exclusive page should not work | Dropdown in Valentines Exclusive page is not working | Pass
Ty_Js_10 | Check whether dropdown in The Big Sale page is working or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page |  | Dropdown in The Big Sale page should not work | Dropdown in The Big Sale page is not working | Pass
Ty_Js_11 | Check whether color dropdown is working properly in each items or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item | Light Range mini halo ruby studs | Color dropdown should work properly in each items | Color dropdown is not working properly in each items | Fail | https://drive.google.com/file/d/1KCqjKSTwNCfKfjqFYQL6PUBAmK4KEjB4/view?usp=sharing

## Cart &Payment
TWENTY ONE JEWELS
Version: |  |  | Environmental Details : Windows 10 |  |  | Tested By: Chandana J S
Verified By: Pradeep K C |  |  | Module Name:Cart &Payment |  |  | Date:28/02/2024
Test Id | Test Description | Test Procedure | Test Data | Expected Result | Actual Result | Result | Screenshots
Ty_Js_01 | Check whether Add to cart button is active or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart |  | Add to cart button should be active | Add to cart button is active | Pass
Ty_Js_02 | Check whether Buy it now button is active or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.But it Now |  | Buy it now button should be active | Buy it now button is active | Pass
Ty_Js_03 | Check whether Add to cart button redirects to cart page or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart |  | Add to cart button should redirects to cart page | Add to cart button is redirecting to cart page | Pass
Ty_Js_04 | Check whether item added to the cart reflects on the cart page or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart |  | Item added to the cart should reflects on the cart page | Item added to the cart is reflecting on the cart page | Pass
Ty_Js_05 | Check whether number of item added to the cart can be updated or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Add number of quantities more than one | Light range 40 Cent solatitare on pure 925 Silver | Number of item added to the cart should be able to update | Number of item added to the cart is able to update | Pass
Ty_Js_06 | Check whethe item added to the cart is reflected properly or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart |  | Item added to the cart should be reflected properly | Item added to the cart is not reflecting properly | Fail | https://drive.google.com/file/d/10OPNoRaosvRO68MK75WKDIlz1E2vNrAg/view?usp=sharing
Ty_Js_07 | Check whethe multiple item can be added to the cart or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select two Items 4.Add to Cart | 1.Premium Range 2 Carat Emerald Cut Princia Solitaire Studs with Screw Backs - White Gold Finish 2.Celery Square Halo 1.3 Carat Premium Solitaire Studs | Multiple item should be able to add to the cart | Multiple item is able to add to the cart | Pass
Ty_Js_08 | Check whethe total price get updated with respect to itwms added or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select two Items 4.Add to Cart | 1.Premium Range 2 Carat Emerald Cut Princia Solitaire Studs with Screw Backs - White Gold Finish 2.Celery Square Halo 1.3 Carat Premium Solitaire Studs | Total price should get updated with respect to items added | Total price is getting updated with respect to items added | Pass
Ty_Js_09 | Check whether Place ur order button is active or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select two Items 4.Add to Cart 5.Click Place ur Order Button |  | Place ur order button should be active | Place ur order button is active | Pass
Ty_Js_10 | Check whether Update Cart button is active or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select two Items 4.Add to Cart 5.Click Update Cart Button |  | Update Cart button should be active | Update Cart button is active | Pass
Ty_Js_11 | Check whether we can updated number of items less than one or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select two Items 4.Add to Cart 5.Update the number of item to zero |  | We not be able to update number of items less than one | We are not able to update number of items less than one | Pass
Ty_Js_12 | Check whether remove item option is active and working properly or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select two Items 4.Add to Cart 5.Remove the Item | Light range 40 Cent solatitare on pure 925 Silver | Remove item option should be active and working properly | Remove item option is active and working properly | Pass
Ty_Js_13 | Check whether Add a note to seller option is active or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Loacte Add a note to Seller option | wadsfvgbh | Add a note to seller option should be active | Add a note to seller option is active | Pass
Ty_Js_14 | Check whether Add a note to seller option get expanded unreadably or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Locate Add a note to Seller option 6.Expand it as possible |  | Add a note to seller option should not get expanded unreadably | Add a note to seller option is getting expanded unreadably | Fail | https://drive.google.com/file/d/1VhULeUz7no2GJxaOLMCiA2NQ1XBCzmHo/view?usp=sharing
Ty_Js_15 | Check whether Item added to the cart redircts to its original item site or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click on the item from the cart page |  | Item added to the cart should redirects to its original item site | Item added to the cart is redirecting to its original item site | Pass
Ty_Js_16 | Check whether any changes in the Item reflects without updating the cart or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Make Changes to item on the cart without clicking update button |  | Any changes in the Item should not reflects without updating the cart | Any changes in the Item is not reflecting without updating the cart | Pass
Ty_Js_17 | Check whether country dropdown is active or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Place ur Order 6.Locate Country Dropdown |  | Country dropdown should be active | Country dropdown is active | Pass
Ty_Js_18 | Check whether First Name field is active or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Place ur Order 6.Locate First Name Field |  | First Name field should be active | First Name field is active | Pass
Ty_Js_19 | Check whether First Name field accept alphabets or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Place ur Order 6.Locate First Name Field | Abin | First Name field should accept alphabets | First Name field is accepting alphabets | Pass
Ty_Js_20 | Check whether First Name field accept numbers or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Place ur Order 6.Locate First Name Field | 123yw | First Name field should not accept numbers | First Name field is accepting numbers | Fail | https://drive.google.com/file/d/1z501QD883uuj-9lrNyq3WvlnHL0nc4D7/view?usp=sharing
Ty_Js_21 | Check whether First Name field accept special characters or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Place ur Order 6.Locate First Name Field | &754$ | First Name field should not accept special characters | First Name field is accepting special characters | Fail | https://drive.google.com/file/d/1hbWbc5QZJJIeyFYuRFyde5F136iUDm72/view?usp=sharing
Ty_Js_22 | Check whether Last Name field is active or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Place ur Order 6.Locate First Name Field |  | Last Name field should be active | Last Name field is active | Pass
Ty_Js_23 | Check whether Last Name field accept alphabets or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Place ur Order 6.Locate Last Name Field | Tony | Last Name field should accept alphabets | Last Name field is accepting alphabets | Pass
Ty_Js_24 | Check whether Last Name field accept special characters or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Place ur Order 6.Locate Last Name Field | gjh$%7 | Last Name field should not accept special characters | Last Name field is accepting special characters | Fail | https://drive.google.com/file/d/1dU6ECyx1RtOUfvYaISrJCrtkT69J7wzC/view?usp=sharing
Ty_Js_25 | Check whether Last Name field accept numbers or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Place ur Order 6.Locate Last Name Field | 34567 | Last Name field should not accept special characters | Last Name field is accepting numbers | Fail | https://drive.google.com/file/d/1FasC733nYOI6RzQVXKHUCbjOe7fa35sS/view?usp=sharing
Ty_Js_26 | Check whether Address field is active or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Place ur Order 6.Locate Address Field |  | Address field should be active | Address field is active | Pass
Ty_Js_27 | Check whether Apartment field is active or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Place ur Order 6.Locate Apartment Field |  | Apartment field should be active | Apartment field is active | Pass
Ty_Js_28 | Check whether Apartment field accept all characters or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Place ur Order 6.Locate Apartment Field | Abin House No98 | Apartment field should accept all characters | Apartment field is accepting all characters | Pass
Ty_Js_29 | Check whether Postal code field is active or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Place ur Order 6.Locate Postal Code Field |  | Postal code field should be active | Postal code field is active | Pass
Ty_Js_30 | Check whether Postal code field accept alphabets or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Place ur Order 6.Locate Postal Code Field | qwe32 | Postal code field should not accept alphabets | Postal code fields is not accepting alphabets | Pass
Ty_Js_31 | Check whether Postal code field accept special characters or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Place ur Order 6.Locate Postal Code Field | *&6 | Postal code field should not accept special characters | Postal code fields is not accepting special characters | Pass
Ty_Js_32 | Check whether Postal code field accept numbers or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Place ur Order 6.Locate Postal Code Field | 3W4 | Postal code field should accept numbers | Postal code fields is accepting numbers | Pass
Ty_Js_33 | Check whether Postal code field accept only postal code format or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Place ur Order 6.Locate Postal Code Field | 691003 | Postal code field should accept only postal code format | Postal code fields is accepting only postal code formats | Pass
Ty_Js_34 | Check whether city field accept all charcters or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Place ur Order 6.Locate city field |  | City field should accept all charcters | City field is accepting all charcters | Pass
Ty_Js_35 | Check whether Phone number field is active or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Place ur Order 6.Locate Phone Number Field |  | Phone number field should be active | Phone number field is active | Pass
Ty_Js_36 | Check whether Phone Number field accept only phone number format or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Place ur Order 6.Locate Phone Number Field | 926825372 | Phone Number field should accept only phone number format | Phone Number field is accepting only phone number format | Pass
Ty_Js_37 | Check whether Payment option is active or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Place ur Order 6.Locate Payment Option |  | Payment option should be active | Payment option is active | Pass
Ty_Js_38 | Check whether save this info checkbox works properly or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Place ur Order 6.Locate Save this Information checkbox |  | Save this info checkbox should works properly | Save this info checkbox is working properly | Pass
Ty_Js_39 | Check whether Text me with news and offers checkbox works properly or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Place ur Order 6.Locate Text me with news and offers checkbox |  | Text me with news and offers checkbox should works properly | Text me with news and offers checkbox is working properly | Pass
Ty_Js_40 | Check whether bank option checkbox is active or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Place ur Order 6.Locate Bank option checkbox in payment |  | Bank option checkbox should be active | Bank option checkbox is active | Pass
Ty_Js_41 | Check whether bank option checkbox redirects to its corresponding page or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Place ur Order 6.Click Bank option checkbox in payment |  | Bank option checkbox should redirects to its corresponding page | Bank option checkbox is redirecting to its corresponding page | Pass
Ty_Js_42 | Check whether online transaction option checkbox redirects to its corresponding page or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Place ur Order 6.Click Online Transaction option checkbox in payment |  | Online transaction option checkbox should redirects to its corresponding page | Online transaction option checkbox is redirecting to its corresponding page | Pass
Ty_Js_43 | Check whether card details field is active in online transaction option or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Place ur Order 6.Click Online Transaction option checkbox in payment 7.Click Debit /credit card option |  | Card details field should be active in online transaction option | Card details field is active in online transaction option | Pass
Ty_Js_44 | Check whether paynow button is active in online transaction with empty fields or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Place ur Order 6.Click Online Transaction option checkbox in payment 7.Click Debit /credit card option |  | Pay now button should not be active in online transaction with empty fields | Pay now button is not active in online transaction with empty fields | Pass
Ty_Js_45 | Check whether COD checkbox is active in online transaction or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Place ur Order 6.Click Online Transaction option checkbox in payment 7.Click Debit /credit card option |  | COD checkbox should be active in online transaction | COD checkbox is active in online transaction | Pass
Ty_Js_46 | Check whether Same as shipping address checkbox is active in online transaction or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Place ur Order 6.Click Online Transaction option checkbox in payment 7.Click Same as shipping address checkbox |  | Same as shipping address checkbox should be active in online transaction | Same as shipping address checkbox is active in online transaction | Pass
Ty_Js_47 | Check whether Use a different billing address checkbox is active in online transaction or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Place ur Order 6.Click Online Transaction option checkbox in payment 7.Click Use a different billing address checkbox |  | Same as Use a different billing address checkbox should be active in online transaction | Same as Use a different billing address checkbox is active in online transaction | Pass
Ty_Js_48 | Check whether Refund Policy page is active or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Place ur Order 6.Click Refund Policy Link |  | Refund Policy page should be active | Refund Policy page is active | Pass
Ty_Js_49 | Check whether Shipping Policy page is active or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Place ur Order 6.Click Shipping Policy Link |  | Shipping Policy page should be active | Shipping Policy page is active | Pass
Ty_Js_50 | Check whether Privacy Policy page is active or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Place ur Order 6.Click Privacy Policy Link |  | Privacy Policy page should be active | Privacy Policy page is active | Pass
Ty_Js_51 | Check whether Terms & Conditions page is active or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Place ur Order 6.Click Terms & Conditions Link |  | Terms & Condition page should be active | Terms & Conditions page is active | Pass

## Loginpage
TWENTY ONE JEWELS
Version: |  |  | Environmental Details : Windows 10 |  |  | Tested By: Chandana J S
Verified By:Pradeep K C |  |  | Module Name:Login Page |  |  | Date:28/02/2024
Test Id | Test Description | Test Procedure | Test Data | Expected Result | Actual Result | Result | Screenshots
Ty_Js_01 | Check whether login link redirects to login page or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Login |  | Login link should redirects to login page | Login link is redirecting to login page | Pass
Ty_Js_02 | Check whether Create Account button is active or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Login 6.Click Create Account Button |  | Create Account button should be active | Create Account button is active | Pass
Ty_Js_03 | Check whether First Name Field is active or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Login 6.Click Create Account Button 7.Locate First Name Field |  | First Name Field should be active | First Name Field is active | Pass
Ty_Js_04 | Check whether First Name Field accepts alphabets or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Login 6.Click Create Account Button 7.Locate First Name Field 8.Enter Test Data | Alice | First Name Field should accept alphabets | First Name Field is accepting alphabets | Pass
Ty_Js_05 | Check whether First Name Field accepts numbers or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Login 6.Click Create Account Button 7.Locate First Name Field 8.Enter Test Data | 124 | First Name Field should not accept numbers | First Name Field is accepting numbers | Fail | https://drive.google.com/file/d/1CekRQKKrh0rqqGQHZ8ZDampLR8D5S34n/view?usp=sharing
Ty_Js_06 | Check whether First Name Field accepts special Characters or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Login 6.Click Create Account Button 7.Locate First Name Field 8.Enter Test Data | &* | First Name Field should not accept special characters | First Name Field is accepting special characters | Fail | https://drive.google.com/file/d/1x7g767reYLd9HfrboNvwQJjazYDpEYgI/view?usp=sharing
Ty_Js_07 | Check whether Last Name Field is active or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Login 6.Click Create Account Button 7.Locate Last Name Field 8.Enter Test Data |  | Last Name Field should be active | Last Name Field is active | Pass
Ty_Js_08 | Check whether Last Name Field accepts alphabets or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Login 6.Click Create Account Button 7.Locate Last Name Field 8.Enter Test Data | Bincy | Last Name Field should accept alphabets | Last Name Field is accepting alphabets | Pass
Ty_Js_09 | Check whether Last Name Field accepts numbers or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Login 6.Click Create Account Button 7.Locate Last Name Field 8.Enter Test Data | 87s | Last Name Field should not accept numbers | Last Name Field is accepting numbers | Fail | https://drive.google.com/file/d/1ppazvQ0UMy438kOaSDX_QTGJLb0OF89u/view?usp=sharing
Ty_Js_10 | Check whether Last Name Field accepts special Characters or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Login 6.Click Create Account Button 7.Locate Last Name Field 8.Enter Test Data | 6% | Last Name Field should not accept special characters | Last Name Field is accepting special characters | Fail | https://drive.google.com/file/d/14bFGEz5EuMU44fhI8iLh2iDKXjThBMC2/view?usp=sharing
Ty_Js_11 | Check whether Create button will be active if any of the field is empty or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Login 6.Click Create Account Button 7.Fill all the field except last name Field | 1.Abin 2.gdhj@gmail.com 3.fghjk&7@ 4.864747478 | Create button should not be active if any of the field is empty | Create button is not active if any of the field is empty | Pass
Ty_Js_12 | Check whether email field is active or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Login 6.Click Create Account Button 7.Locate Email Field |  | Email field should be active | Email field is active | Pass
Ty_Js_13 | Check whether email field accept only email format active | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Login 6.Click Create Account Button 7.Click Email Field 8.Enter Test Data | 1.tghjk@gmail.com 2.dfghjk | Email field should accept only email format active | Email field should accept only email format active | Pass
Ty_Js_14 | Check whether password field is active or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Login 6.Click Create Account Button 7.Locate Password Field |  | Password field should be active | Password field is active | Pass
Ty_Js_15 | Check whether password field accept all characters or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Login 6.Click Create Account Button 7.Click Password Field 8.Enter Test Data | TwentyOneJewels45@ | Password field should accept all characters | password field is accepting all characters | Pass
Ty_Js_16 | Check whether password field accept password less than five characters or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Login 6.Click Create Account Button 7.Click Password Field 8.Enter Test Data | 1.dfg 2.dfghj% | Password field should not accept password less than five characters | Password field is not accepting password less than five characters | Pass
Ty_Js_17 | Check whether phone number field is active or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Login 6.Click Create Account Button 7.Locate Phone Number Field |  | Phone number field should be active | Phone number field is active | Pass
Ty_Js_18 | Check whether phone number field accept phone number format only or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Login 6.Click Create Account Button 7.Click Phone Number Field 8.Enter Test Data | 9876543210 | Phone number field should accept phone number format | Phone number field is accepting phone number format | Pass
Ty_Js_19 | Check whether create button is active or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Login 6.Click Create Account Button 7.Locate Create Button |  | Create button should be active | Create button is active | Pass
Ty_Js_20 | Check whether Sign In button is active or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Login 6.Click Create Account Button 7.Locate Sign In Button |  | Sign In button should be active | Sign In button is active | Pass
Ty_Js_21 | Check whether Sign In button is active if we give wrong credentials or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Login 6.Click Create Account Button 7.Click Sign In Button 8.Enter Test Data | 1.sdfvgbhnjk@gmail.com 2.Wxdcfvghb^ | Sign In button should not be active if we give wrong credentials | Sign In button is not active if we give wrong credentials | Pass
Ty_Js_22 | Check whether logout link is active or not |  |  | Logout link should be active | Logout link is active | Pass
Ty_Js_23 | Check whether logout link is working properly and gets logout from the session or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Login 6.Click Create Account Button 7.Click Sign In Button 8.Enter Test Data 9.Click Logout Button | 1.sdfvgbhnjk@gmail.com 2.Wxdcfvghb^ | logout link should be working properly and gets logout from the session | logout link is working properly and gets logout from the session | Pass
Ty_Js_24 | Check whether reset ur password link is working and enter ur email field is active or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Login 6.Click Create Account Button 7.Click Sign In Button 8.Click reset ur Password |  | Reset ur password link should be working and enter ur email field is active | Reset ur password link is working and enter ur email field is active | Pass
Ty_Js_25 | Check whether submit button is active or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Login 6.Click Create Account Button 7.Click Sign In Button 8.Click reset ur Password 9.Click Submit Button |  | Submit button should be active | Submit button is active | Pass
Ty_Js_26 | Check whether Conitnue as a guest button is active or not | 1.Open TwentyOneJewels Website 2.Click The Big Sale page 3.Select an Item 4.Add to Cart 5.Click Login 6.Click Create Account Button 7.Click Conitnue as a Guest Button |  | Conitnue as a guest button should be active | Conitnue as a guest button is active | Pass
Ty_Js_27 | Check whether Chat with us button is active or not | 1.Open TwentyOneJewels Website 2.Click Chat with Us |  | Chat with us button should be active | Chat with us button is active | Pass

## Bug Report
TWENTY ONE JEWELS
Version: |  | Environmental Details : Windows 10 |  | Tested By: Chandana J S
Verified By:Pradeep K C |  | Module Name: Twenty One Jewels Website | :Twenty One Jewels Website | Date: | Date:28/02/2024
Bug Id | Bug Description |  | Priority | Severity | Status
Def_RF_TY_01 | Account icon is not working |  | Major | High | New
Def_RF_TY_02 | Account icon is not redirecting to its corresponding next page |  | Major | High | New
Def_RF_TY_03 | Place Order Button is not active while selection |  | Minor | Medium | New
Def_RF_TY_04 | Place Order Button is redirecting even though cart is empty |  | Minor | Medium | New
Def_RF_TY_05 | Pick ur Evil eye button is not visible while selection |  | Minor | Low | New
Def_RF_TY_06 | Side arrow for image sliding is working properly |  | Minor | Low | New
Def_RF_TY_07 | Connect with priyanka button is not working |  | Major | Medium | New
Def_RF_TY_08 | Connect with priyanka button is not visible while selection |  | Minor | Low | New
Def_RF_TY_09 | Get Direction button is not visble while selection |  | Minor | Low | New
Def_RF_TY_10 | Get Direction button shows wrong location |  | Major | High | New
Def_RF_TY_11 | Name Field in Contact Us accept special characters |  | Minor | Medium | New
Def_RF_TY_12 | Name Field in Contact Us accept numbers |  | Minor | Medium | New
Def_RF_TY_13 | Name Field in Contact Us accept empty fields |  | Minor | Medium | New
Def_RF_TY_14 | PhoneNumber in Contact Us accept less than 10 digits |  | Minor | High | New
Def_RF_TY_15 | Send button is not active while selection |  | Minor | Low | New
Def_RF_TY_16 | Send button is active with empty fields |  | Major | Medium | New
Def_RF_TY_17 | Filter Dropdown has spelling errors |  | Trivial | Medium | New
Def_RF_TY_18 | Filter Dropdown is not alphabetically arranged format |  | Enhancement | Low | New
Def_RF_TY_19 | Alphabetically A-Z option in dropdown doesn’t arranged in that format |  | Minor | High | New
Def_RF_TY_20 | Some Items has prices less than or equal to zero |  | Major | High | New
Def_RF_TY_21 | All Images of the item is not displayed in Big Sale Page |  | Minor | Medium | New
Def_RF_TY_22 | All Images of the item is not displayed in Valentines Exclusive Page |  | Minor | Medium | New
Def_RF_TY_23 | Duplication of option is present |  | Major | Low | New
Def_RF_TY_24 | Some options in dropdown doesn't work properly |  | Minor | Medium | New
Def_RF_TY_25 | Colour dropdown is not working properly |  | Minor | Medium | New
Def_RF_TY_26 | Item added to cart is not reflected properly |  | Major | High | New
Def_RF_TY_27 | Add a note to seller expands unreadabily |  | Minor | Low | New
Def_RF_TY_28 | First Name Field accept numbers |  | Minor | Medium | New
Def_RF_TY_29 | First Name Field accept special Characters |  | Minor | Medium | New
Def_RF_TY_30 | Last Name Field accept numbers |  | Minor | Medium | New
Def_RF_TY_31 | Last Name Field accept special Characters |  | Minor | Medium | New
Def_RF_TY_32 | First Name Field accept numbers in login page |  | Minor | Medium | New
Def_RF_TY_33 | First Name Field accept special Characters in login page |  | Minor | Medium | New
Def_RF_TY_34 | Last Name Field accept numbers in login page |  | Minor | Medium | New
Def_RF_TY_35 | Last Name Field accept special Characters in login page |  | Minor | Medium | New

## Test Summary
TWENTY ONE JEWELS
Module Name | Testcase Passed | Testcase Failed | Total TestCases
HomePage | 45 | 16 | 61
Category & Collection | 38 | 4 | 42
Collection Pages | 6 | 5 | 11
Cart & Payment | 47 | 6 | 53
LoginPage | 23 | 4 | 27